SELLINDGE PRIMARY SCHOOL - GOVERNING BODY DEVELOPMENT PLAN - SEP 2022 – AUG 2024

This plan is intended to ensure that the FGB’s activities are focussed on supporting and challenging the school’s leaders (at all levels) in achieving the key strategic priorities for the school, as identified in the School Improvement Plan (which reflects the findings of external inspections and visits -  the Ofsted report of 2009 and ongoing LA support – and the school leaders’ own assessments of school needs) and that the FGB has the capacity and skills to do so.

NOTE: The FGB recognises its statutory obligations in relation to safeguarding, access to education for all, and finance. In so far as these may not currently feature as a focus area in this edition of the FGB’s plan, they are, however, included in the scope of work carried out by the relevant, delegated governor sub-groups of the circle model used currently for monitoring (including Safeguarding, Financial health / propriety / value for money, SEN, Health & Safety, Inclusion and Pupil Premium / PE Premium / Disadvantaged Pupils), and during (in)formal visits carried out by Governors generally. All such reports must be placed on an FGB meeting agenda and are open to scrutiny and further challenge / questions by any governor(s) in accordance with the monitoring schedule and as evidenced in FGB minutes ongoing. Governors also maintain and review statutory policies in these key areas and others, as appropriate. The Chair and Vice Chair ensure a clear separation exists between strategic (Governors and SLT) and operational (SLT and Subject Leaders) leadership in the school, which is supported by positive relationships that encourage a professional culture and ethos throughout.

This plan reflects the structure of the ‘The key features of effective governance’ and this plan sets out development actions for the FGB and assesses the effectiveness of Governors’ implementation and impact of their actions under the respective headings. All governors receive and sign the Code of Conduct as part of their induction and updates are assessed annually.

This plan is to be formally monitored seasonally (or as otherwise provided in each section) but is a standing item on the FGB agendas, should governors in the interim wish to contribute and/or update areas, actions or evidence.

For ease of reference the key elements / targets of the 2009 Ofsted report are set out below:

Ofsted Report 2009

What does the school need to do to improve further?

“Increase pupils' understanding of the varied lives, beliefs and cultures of children in other areas of the UK for example by making links to other schools.”

,

| - Strategic Leadership that sets and champions vision, ethos and strategy |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost (if app.) | Deadline | Success Criteria / Evidence |
| 1a. The Governing Body 5-Year Vision is reviewed annually. 1b. Leaders regularly consider when to initiate strategic change. | 5-Yr Strategic Vision Plan reviewed annually. 1 and 3 Yr plans in place (strategic and operational) – with milestones, wherever possible Managing the ongoing expansion of school places. Stay abreast of the latest trends and recommendations for strategic school governance leadership | Chair / FGB HT / FGB Chair / HT / FGB FGB | £Nil 1-2 days | Term 1 FGB meeting Term 1 FGB meeting | Website Reviewed annually and used to guide action elsewhere. Governor development plan supports this. School Improvement Plans Self-Evaluation Form Minutes of FGB Minutes Monitoring reports. Training feedback / reports from Clerk and Governors Headteacher’s report HT and Govs attend training and remain networked in local and regional developments (i.e. Otterpool). FGB receives advice and information as conditions change. |
| Concluding comments: |  |  |  |  |  |

| - Accountability that drives up education standards and financial performance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost | Deadline | Success Criteria / Evidence |
| 1a. The schools’ paid leaders (of all levels) are supported and challenged in achieving their declared action / development plans. 1b. There is a rigorous analysis of pupil progress and attainment information and comparison against national benchmarks over time. | All school leaders are able to engage with strategic questions and welcome the opportunities to describe their progress / impacts. Dedicated time for analysis of summer / other results, and at other times in HT reports and monitoring. | Chair / FGB / SLT HT/FGB | Varied – see individual action / development plans. | Ongoing FGB & Monitoring Meetings with HT reports and following pubic examination data release | Governor Minutes HT Reports Other reports (such as those from Middle Leaders presented to governors) Monitoring Reports (In)formal Reports of Visits by governors Notes of Visit (LA) Subject area Impact Statements Governor minutes HT reports Monitoring activities Other reports and presentations |
| 2a. There is a transparent system for performance management of school leaders linked to strategic priorities. 2b. There is an effective oversight of performance and the framework for the pay and conditions of service for all other employees. | Annual review of Pay Policy Annual review of Appraisal Policy Annual delegation of HT Appraisal to a named committee Policy and practice review to take place in the autumn. Staff consulted on the effectiveness of the policies. | Chair / FGB Chair / FGB / HT | Nil | FBG meetings (following Monitoring schedule) Ongoing | Minutes of FGB meeting term 2 Policies in place External LA comments on HT appraisal HT Appraisal systems regularly reviewed for robustness HT Appraisal committee named (comprising three governors) LA / SPS policies and practices guidance are used |
| 3. Governors are aware of and prepared for formal external scrutiny. | Training as appropriate, including updates in governor meetings. Following initial report from HT, Governors evaluate the ongoing work of the school in addressing the key issue from the previous Ofsted inspection report to 'Increase pupils' understanding of the varied lives, beliefs and cultures of children in other areas of the UK for example by making links with other schools.' | FGB / Training & Development Governor HT / FGB | LA training package as part of the SLA (considered) SMSC Standards / Kitemark | Ongoing Term 2 2022 FGB and completed by end of this development plan cycle. | Priority areas standing items in FGB meetings. Minutes of meetings Training record SMSC Kitemark standards to be used to audit current gaps and intensive action to be taken. Headteacher to present to governors on progress / impact. |
| Concluding comments: |  |  |  |  |  |

| - People with the right skills, experience, quality and capacity |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost | Deadline | Success Criteria / Evidence |
| 1. Governors understand the purpose of governance and have completed a skills audit that is reviewed regularly. | Training programme is based on skills, knowledge and experience. School Plan needs are linked to Governor Training, where available | Training and Development Governor / FGB / Clerk | LA training package as part of the SLA | Annual programme | Training record Completed skills audit Evaluations of training |
| 2. There is an effective Chair, Vice-Chair and Clerk in place. | Elections held at first meeting in term 1 Chair, Vice Chair and Clerk ask for feedback on performance at least biannually (or when replaced in role, whichever is sooner), using NGA role competencies framework. | Chair / HT / Clerk Chair / VC / Clerk | Nil | Term 1 meeting Term 3 | Chair and Vice-Chair elected Current Chair has completed Leadership Development programme for Chairs – others regularly encouraged Minutes of FGB meeting Training undertaken under SLA Chair or Vice Chair meet governors for regular 1-to-1 review. |
| 3a. Governors offer a diversity of perspectives to enable robust decision-making. 3b. There is succession planning in place for the Chair / Vice-Chair roles | All governors contribute to governor meetings. Governors are encouraged to apply for the Chairs' Development Programme funding, whenever available. | Chair / Vice Chair / FGB | Nil | All meetings Term 6 annually | Minutes of meetings reflect discussion, rigour and challenge Vacancies are filled (e.g. using Inspiring Governance) and Associate Governor members encouraged. Governors who would like to be Chair have undertaken / are undertaking the L3 NGA / LG Chairs’ Development Programme, or have other experience. This is not compulsory. |
| 4. There is an effective clerk to provide expert advice and guidance to ensure the efficient and compliant operation of the governing body. | Clerk attends clerk briefings. Clerk regularly checks appropriate websites, DfE, local authority briefing papers, regarding changes to legislation / policy / compliance. | Chair / Clerk | Nil | Ongoing | Appraisal of clerk. Clerk continues to seek and monitor own CPD needs. Clerks stays abreast of the latest trends, advice and approaches to governance. |
| Concluding comments: |  |  |  |  |  |

| - Structures that reinforce clearly defined roles and responsibilities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost | Deadline | Success Criteria / Evidence |
| 1. There are appropriate monitoring pairs in place with defined roles in line with the circle model of governance adopted. | Review terms of reference. Review the effectiveness of the circle model and specific areas of responsibility. Consult governors for new skills development | FGB | Nil | FGB meeting in term 1 Term 5 annually Biannually, or sooner where need dictates | Minutes of FGB meeting Minutes Governors consulted on monitoring structure and CPD needs are discussed at review. |
| 2. There are processes for ensuring good communication between all governors and to pupils, parents, staff and community. | Consider implementing a governor communication strategy / policy Governors should be proactive as introducing themselves as such when engaging with key stakeholders in order to elicit appropriate feedback and views, as well as to inform | FGB / Clerk | Nil | Regular updates on Governance section of the website. | Feedback from advisers Governors are routinely present at Parents' Evenings and many other events in their capacity as a Governor – see Informal Visits list shared with FGB and dates/events featured in the Swan. FGB updates online, in The Swan, as well as in a bi-annual Governors’ Newsletter. Parents are encouraged to complete Ofsted Parent View. Documents for FGB meetings are available at least 7 days before each meeting where questions should be raised. |
| Concluding comments: |  |  |  |  |  |

| - Compliance with statutory and contractual requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost | Deadline | Success Criteria / Evidence |
| 1. Governors are aware of their responsibilities under education and employment legislation, paying due regard to statutory and contractual responsibilities. | Make checks through monitoring activities and compliance items of FGB agendas | Chair / Clerk / HT | Nil | Ongoing | Minutes of FGB meetings Monitoring reports Clerk advice heeded. |
| 2. Governors understand their responsibilities under the Equalities Act, promoting equality and diversity throughout the school. | Check Public Sector Duty completed, on website. Compliance checks. | Chair / Clerk / HT | Nil | Annually by term 4 | Minutes of meetings Policies. Clerk advice heeded. |
| Concluding comments: |  |  |  |  |  |

| - Evaluation to monitor and improve the quality and impact of governance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Action | Lead | Cost | Deadline | Success Criteria / Evidence |
| 1. We have an appropriate induction for those new to governance. | Induction pack in place online. SLA - Local Authority training Initial meetings with (vice) chair and allocation of one-to-one support session (inc. being allocated to existing monitoring pairs) | Clerk / Chair / Vice Chair / HT / FGB | SLA | As and when needed | Log–in provided to Governor site Registration with Local Authority Platform folder with useful orientation documents. Induction training encouraged. One-to-one support session with (Vice) Chair for new governors. |
| 2a. We undertake skills audits to identify skills and knowledge gaps and inform CPD. 2b. We have processes for self-evaluation in terms of operation and effectiveness. | All governors complete skills audit. Training programme in place. Training attendance monitored FGB to conduct regular self-evaluation | Clerk / Training & Development Governor / FGB / Chair | SLA Nil | Biannually or sooner, if justified (i.e. by FGB changes) Annually Ongoing | Completed skills audit in place Training record and evaluations. T&D Governor recommendations in minutes. Updated Governor Development Plan Completed self-evaluations Training records Updated Governing Body Healthcheck (by all) inc. standing order items |
| 3. Our minutes and monitoring accurately capture evidence of decisions and impact. | Regularly RAG new ofsted criteria for good/outstanding - evidence of discussions. Colour-coding for challenge, scrutiny, probing questioning. ALWAYS look to support the SLT, staff, pupils and parents. Awareness of Governor / staff workload / quality of life – inc. that of the senior executive. | Chair / HT / FGB | Nil Possible funding avenues found by Governor(s) | Ongoing | Governor minutes – challenge highlighted. RAGed Ofsted criteria Standing item for training (Ofsted) Monitoring feedback to FGB – further questions Data / Progress indicators interrogated (e.g. minutes / QoE) Governors have advised on / sought / secured funding sources for the school Standing item. |
| Concluding comments: |  |  |  |  |  |

| - Elements identified as ‘red’ by the governing body from the Governorhub Healthcheck (2021-2): |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area number and descriptor | Action Needed or elements to move the area to amber / green. | Lead | Cost | Deadline | Success Criteria / Evidence |
| 4. Governors have agreed high expectations of behaviour and conduct which are described by published principles and policies for behaviour. The pupils are aware of expectations and this is reflected in their conduct, attendance and punctuality. (Behaviour & Attitudes) | Review behaviour policy Carry out monitoring / including ‘learning walk’ to see policy in action. | Clerk / FGB |  | Term 6 2023 | Policy reviewed Monitoring carried out / shared with FGB – Qs taken. Annual focus for monitoring in Governor Day |
| 7. We have seen evidence that teachers in our school(s) present subject matter clearly, promoting appropriate discussion about the subject matter they are teaching. They check learners’ understanding systematically, identify misconceptions accurately and provide clear, direct feedback. In doing so, they respond and adapt their teaching as necessary, without unnecessarily elaborate or differentiated approaches. (QE Implementation) | SLT to invite governors to key aspects of their internal monitoring systems in order to impart this knowledge to governors. | HT / Middle Leaders / FGB |  | Term 6 2023 | Governors have continued to receive impact statements verbally at meetings on a rotation basis. Governors have read all subject area impact statements available on the platform (to be kept up to date by HT). Governors have accepted invitations to accompany SLT in guided learning walks, pupil voice, and guided work scrutiny, etc. Monitoring feedback in this area should be shared at FGB meetings and minuted. |
| 10. We know that learners’ attitudes to their education or training are positive. They know how to study effectively and are resilient to setbacks and take pride in their achievements. The relationships among learners and staff reflect a positive and respectful culture. Leaders, teachers and learners create an environment where bullying, peer-on-peer abuse or discrimination are not tolerated. (Behaviour & Attitudes) | Governors to complete a piece of pupil voice work on these topics. SLT to have the opportunity to evidence this area in a FGB meeting as they see fit. | FGB / Staff |  | Term 4 2023 | Monitoring and minutes reflect that this work has been undertaken and that key Qs have been asked. SLT should be challenged on any emergent / significant identified areas of need. |
| 13. We ensure that staff have opportunities to develop their subject and pedagogical knowledge. We are realistic and constructive in understanding and addressing the pressures on our staff, including their workload. We ensure that leaders protect staff from bullying and harassment. (Leadership & Management) | Use questionnaires to gather staff views and HT to create follow-up face-to-face opportunity to discuss findings. FGB receives this information via Headteacher report or other evidence as SLT sees fit. | FGB / HT / Staff |  | Ongoing – every two years Term 3 2023 Ongoing | Governors have surveyed the staff in this area, inc. at the Governor Day. Governors have a standing item on workload / wellbeing of staff and take action, where relevant. Minutes show that governors have received an account of how the SLT ensures that staff are protected from bullying and harassment. Headteacher’s report continues to report on CPD undertaken by staff |
| Concluding comments: |  |  |  |  |  |